## Epics
Epic Id | Epic Name | Description
FB001-1 | Implement Fakebook Application Core Features | This is the foundation for the entire application, including some necessary features like authentication, building the common Library, EF core base setup, Dockerize service, Manage Development Environment by Docker compose, Setting up API Testing, Preparing Kubernetes Environment, CI/CD
FB001-2 | Implement User Relationship Features | The context of this epic is to build page, so user to be able to access to the own profile page, and can make request to create a relationship with anyone
FB001-15 | Implement the UI Service by React TypeScript | Build the core UI Service by using ReactTS, using Redux Zero to manage State more effectively, containerizing the application to Images, building CI/CD for the FE service to deploy the Staging and Production environment
4
5
6
7
8

## FB001-1
Implement Fakebook Application Core Features
Ticket Id | Ticket Name | Ticket Description | Task Id | Task Name | Task Description
SCRUM-3 | Create User service for authentication | Create a first service running at local development within docker, support authentication via JWT, and Clean Code by creating a .NET Library | SCRUM-8 | Create the First ASP .Net Core API Application within connecting to SQL server | - Create the First ASP .Net Core API Application running locally - Create the SQL Server running on Docker and connect to it from the API server - Implement Repository and UnitOfWork design pattern - Using Postman to test API
|  |  | SCRUM-9 | Design User table and implement Authentication via JWT | - Using EF Core Code First to Design Authentication Table - Implement a feature to authenticate via JWT
|  |  | SCRUM-10 | Optimize and Clean Code by creating .Net Library | - Create Dotnet Library for UnitOfWork and Repository pattern
SCRUM-4 | Containerize User service and Orchestrate with Docker Compose | Containerize User application service and run on Docker by using Docker Compose
SCRUM-5 | Create Automation Testing for API for User service | Using Postman to create the scenario for automation API testing, and using Newman to test this collection
SCRUM-6 | Deploy the User service to the Kubernetes Cluster | Using Vagrant to build the Cluster and deploy the User service to the Kubernetes Cluster | SCRUM-11 | Using Vagrant to build Cluster | Using Vagrant tool to automatically build the Cluster with 3 Nodes
|  |  | SCRUM-12 | Deploy User service to Kubernetes Cluster | Create the yaml script file and manually deploy to this Cluster
SCRUM-7 | Create CI/CD for the user service | Create the CI/CD to automate deploy the User service to Kubernetes Cluster and Run the script before deploying | SCRUM-13 | Build the Jenkins running on Docker | Using Docker to build the Jenkins applications
|  |  | SCRUM-14 | Create CI/CD pipeline to automate User service deployment | Setup Jenkins and create the pipeline to automate User service deployment

## FB001-15
Implement the UI Service by React TypeScript
Ticket Id | Ticket Name | Ticket Description | Task Id | Task Name | Task Description
SCRUM-16 | Setup UI and Install Packages, Clean Code | Set up UI project and install some necessary Packages, set up Redux to manage state and hooks. Redux-Thunk | SCRUM-23 | Install the first UI project | Setup UI project and install some necessary Packages
|  |  | SCRUM-29 | Create a Login UI page with Role base routing | Create the first Login page with the necessary animation by using react. Permission base basic for routing the user, Create AdminLayout and MemberLayout and permission needed for routing
|  |  | SCRUM-24 | Setup Redux | Install and setip basic Redux
|  |  | SCRUM-25 | Research React Hook | Research the hook basic and advance
|  |  | SCRUM-26 | Setup Middleware by using Redux-Thunk | Install and setup basic middleware by using Redux-Thunk
SCRUM-17 | Create Login Page | Create login page to Interact with User service API to indicate whether this use is authenticated or not, using localStorage to store the JWT token
SCRUM-18 | Containerize the application | Containerize the UI application to the images and run it by using Docker Compose
SCRUM-19 | Create CI/CD to deploy to Cluster for two environments | Create Jenkins Job to automate deployment for UI project
SCRUM-20 | UAM for user based on Role base | Create User Access Management to allow user access to the page based on their Rolex, and define some basic Account, Role | SCRUM-27 | Update User service to support Role Base communication | Update User service and Database to support Role Base access to the application, and define some fixed Account, Role (Admin, User, Guest) by script
SCRUM-21 | Error handling | Routing the user to the Error page when they face an error | SCRUM-28 | UAM routing on UI | Create the UI to be able to access the acceptable page based on their role
SCRUM-22 | Clean Code