## Epics
Epic Id | Epic Name | Description
SCRUM-1 | Implement Fakebook Application Core Features | This is the foundation for the entire application, including some necessary features like authentication, building the common Library, EF core base setup, Dockerize service, Manage Development Environment by Docker compose, Setting up API Testing, Preparing Kubernetes Environment, CI/CD
SCRUM-2 | Implement User Relationship Features | The context of this epic is to build page, so user to be able to access to the own profile page, and can make request to create a relationship with anyone
3
4
5
6
7
8

## SCRUM-1
Implement Fakebook Application Core Features
Ticket Id | Ticket Name | Ticket Description | Task Id | Task Name | Task Description
SCRUM-3 | Create User service for authentication | Create a first service running at local development within docker, support authentication via JWT, and Clean Code by creating a .NET Library | SCRUM-8 | Create the First ASP .Net Core API Application within connecting to SQL server | - Create the First ASP .Net Core API Application running locally - Create the SQL Server running on Docker and connect to it from the API server - Implement Repository and UnitOfWork design pattern - Using Postman to test API
|  |  | SCRUM-9 | Design User table and implement Authentication via JWT | - Using EF Core Code First to Design Authentication Table - Implement a feature to authenticate via JWT
|  |  | SCRUM-10 | Optimize and Clean Code by creating .Net Library | - Create Dotnet Library for UnitOfWork and Repository pattern
SCRUM-4 | Containerize User service and Orchestrate with Docker Compose | Containerize User application service and run on Docker by using Docker Compose
SCRUM-5 | Create Automation Testing for API for User service | Using Postman to create the scenario for automation API testing, and using Newman to test this collection
SCRUM-6 | Deploy the User service to the Kubernetes Cluster | Using Vagrant to build the Cluster and deploy the User service to the Kubernetes Cluster | SCRUM-11 | Using Vagrant to build Cluster | Using Vagrant tool to automatically build the Cluster with 3 Nodes
|  |  | SCRUM-12 | Deploy User service to Kubernetes Cluster | Create the yaml script file and manually deploy to this Cluster
SCRUM-7 | Create CI/CD for the user service | Create the CI/CD to automate deploy the User service to Kubernetes Cluster and Run the script before deploying | SCRUM-13 | Build the Jenkins running on Docker | Using Docker to build the Jenkins applications
|  |  | SCRUM-14 | Create CI/CD pipeline to automate User service deployment | Setup Jenkins and create the pipeline to automate User service deployment

## Sheet4
Implement User Relationship Features
Ticket Id | Ticket Name | Ticket Description | Task Id | Task Name | Task Description